## Tabelle1
Arbeitsschritt | Bemerkung | Deadline | Erledigt
DataIO
| Upload Census (name: census, geopandas.GeoDataFrame()). | 2018-02-22
| Upload Gis-Data Niedersachsen (WGS 84, name: gis_road, gis_buildings, …, geopandas.GeoDataFrame()). Lukas about relevant data. | 2018-02-22
Conditioning
| Calculate centroid of area of census raster. | 2018-02-26
| Transform Gis-Data into graph (WGS 84, name: G, networkx.Graph()). | 2018-03-01
| Transform Census from EPSG 3035:into EPSG:4326 on demand. | 2018-02-26
| Calculate best way of sewage to wastewater treatment plant from all edges at least once. | 2018-03-10
Sort all nodes by longest way from sewage plant. This will be needed for cummulating waster water flows along the paths.
Allocation
| Calculate for each raster centroid the waster water flow. Inhabitans * waster water flows + special buildings? | 2018-03-11
| Allocate centroids to nearest node and cumulate their sewage flows along shortest path. Save result into nx.set_node_attribute(G, “sewage_flows“) | 2018-03-15
Calculation
| Cumulate sewage flows of nodes along best way to wastewater treatment plant. | 2018-03-20