## Tabelle1
Arbeitsschritt | Bemerkung | Deadline | Erledigt
DataIO
| Upload Census (name: census, geopandas.GeoDataFrame()). | 2018-02-22
| Upload Gis-Data Niedersachsen (WGS 84, name: gis_road, gis_buildings, …, geopandas.GeoDataFrame()). Lukas about relevant data. | 2018-02-22
Conditioning
| Calculate centroid of are size of buildings. | 2018-02-26
| Save them as gis_buildings[“centroid“] (Point(x,y) and gis_buildings[“iPsqm“] (float). | 2018-02-26
| Transform Gis-Data into graph (WGS 84, name: G, networkx.Graph()). | 2018-03-01
| Transform Census from EPSG 3035:into EPSG:4326 on demand. | 2018-02-26
| Calculate best way of sewage to wastewater treatment plant from all edges at least once. | 2018-03-10
Allocation
| Allocate inhabitants of census 100 x 100 sqm with git_buildings['iPsqm']. Save it in gis_buildings[“inhabitants“]. | 2018-03-11
| Multiply gis_buildings[“inhabitants“] with key figure „wastewater flow per sqm“. Save result into gis_buildings[“sewage_flow“]. | 2018-03-11
| Allocate centroids to nearest edge and cumulate their sewage flows. Save result into nx.set_node_attribute(G, “sewage_flows“) | 2018-03-15
Calculation
| Cumulate sewage flows of edges along best way to wastewater treatment plant. | 2018-03-20